## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 1 | 0 | 1 | 0 | 0 | 0
| Project title: | Absence of insights for the relationship between student's economic background. |  | Intern Id: | IP-5911 | Project Manager: | Harshada Topale |  |  | Assumption | 1 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 1 | 0 | 1 | 0 | 0 | 0
| DOCUMENT VERSION: | 2 |  | Last Updated date: | 2025-02-28 | Project Team Lead: | NA |  |  | Dependency | 1 | 0 | 1 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 4 |  |  |  |  | 3
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Lack of accurate economic background data | Data inconsistency may affect insights | Validate data sources and clean inconsistencies | Data Analyst | High | High | Open | Risk
2 | Assumption | Students' salary expectations are based on academic performance and skills | May not reflect real-world job market trends | Compare survey results with market salary data | Research Team | Medium | Low | Open | Assumption
3 | Issue | Missing or incomplete data for some students | Could lead to biased insights | Use interpolation techniques or exclude unreliable data | Data Team | High | Moderate | Open | Issue
4 | Dependency | Industry salary data availability | Project insights depend on external reports | Acquire reliable market salary reports | Project Manager | High | High | Open | Dependency
5
6 | [8 empty] | Open
7 | [8 empty] | Closed
8
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24