## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Plan
PROJECT PLAN
DOCUMENT VERSION: 1.0
PROJECT NAME | Absence of insights for the relationship between student's economic background.
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Project Charter, SRS, WBS, RAID logs, Lesson Learnt, Progress Report
PROJECT SCOPE
PROJECT START DATE | 2024-12-13
PROJECT END DATE | 2025-02-28
OVERALL PROGRESS | Completed
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1. Initiation
1.1 | Identify key objectives (impact of background on performance) | Data Analyst (Rupali) | 2025-02-01 | 2025-02-02 | 2 | COMPLETED
1.2 | Collect student background & performance dataset |  | 2025-02-03 | 2025-02-05 | 3 | COMPLETED
1.3 | Define research questions & hypothesis | Project Manager | 2025-02-06 | 2025-02-07 | 2 | COMPLETED
1.4 | Identify key stakeholders (schools, students, institutions) | Data Team | 2025-02-08 | 2025-02-09 | 2 | COMPLETED
2. Planning
2.1 | Select tools for analysis (Excel, SQL, Power BI) | Data Analyst | 2025-02-10 | 2025-02-12 | 3 | COMPLETED
2.2 | Define data cleaning & processing steps | Data Analyst | 2025-02-13 | 2025-02-14 | 2 | COMPLETED
3. Execution
3.1 | Data Cleaning & Transformation | Data Analyst | 2025-02-15 | 2025-02-18 | 4 | COMPLETED
3.2 | Exploratory Data Analysis (EDA) | Data Analyst | 2025-02-19 | 2025-02-22 | 4 | IN PROGRESS
3.3 | Feature Engineering (selecting key attributes) | Data Analyst | 2025-02-23 | 2025-02-24 | 2 | PENDING
3.4 | Building Data Visualization Dashboard | Data Analyst | 2025-02-25 | 2025-02-26 | 1 | PENDING
4. Testing & Validation
4.1 | Validate dataset completeness |  | 2025-02-27 | 2025-02-28 | 1 | PENDING
4.2 | Check dashboard accuracy |  |  |  |  | PENDING
5. Closure
5.1 | Present findings & insights | Data Analyst | 2025-02-28 |  |  | PENDING
5.2 | Document recommendations for education policy | Project Manager |  |  |  | PENDING